2014 CCYS ROLL-OUT FACILITATION PLAN

Goal:

Increase 2014 Caring Communities Youth Survey (CCYS) response rate in New Orleans to at least 70%.  (2012 response rate: 17%)

Objectives:

Objective 1: Clarify CCYS administration process and identify barriers to response.

- Meet with Picard Center staff to discuss survey administration process (Feb. 2014)

- Develop plan to address barriers to response (Feb. 2014)

Objective 2: Conduct outreach to improve school participation.

- Meet with RSD, OPSB, and Archdiocese leadership to discuss CCYS and obtain district-level support (Mar. 2014)

- Develop communications materials to support CCYS implementation (Mar. – May 2014)

- Identify CCYS Coordinator at every school in New Orleans and obtain school-level support (Apr. – May 2014)

Objective 3: Assist with 2014 CCYS administration as appropriate.

- Train school CCYS Coordinators and other school staff in survey administration (Jul. – Sep. 2014)

- Administer CCYS, providing staffing support to schools as necessary (Oct. – Nov. 2014)

- Monitor survey response (Oct. – Dec. 2014)

Project Timeline:

| Implementation Activity | Status | Month |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Clarify CCYS administration process and identify barriers to response. |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC |
| Meet with Picard Center staff to discuss survey administration process | Complete |  | X |  |  |  |  |  |  |  |  |  |  |
| Develop plan to address barriers to response | Ongoing |  | X |  |  |  |  |  |  |  |  |  |  |
| Goal 2: Conduct outreach to improve school participation. |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC |
| Meet with RSD, OPSB, and Archdiocese leadership to discuss CCYS and obtain district-level support | In progress Need meeting with Archdiocese |  |  | X |  |  |  |  |  |  |  |  |  |
| Develop communications materials to support CCYS implementation | Ongoing CCYS one-pager exists – continually updated for different target audiences |  |  | X | X | X |  |  |  |  |  |  |  |
| Present on CCYS at RSD monthly CMO meeting and OPSB monthly principals meeting | In progress Awaiting dates from districts |  |  |  |  | X |  |  |  |  |  |  |  |
| Outreach to policy makers, education advocates (e.g. Urban League, Cowen Institute, New Schools for New Orleans, OPEN, etc.) | In progress Need to make list of all orgs. we want to target |  |  | X | X | X | X |  |  |  |  |  |  |
| Identify CCYS Coordinator at every school in New Orleans and obtain school-level support | Not started To begin following CMO/principals meetings |  |  |  | X | X | X |  |  |  |  |  |  |
| Goal 3: Assist with 2014 CCYS administration as appropriate. |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC |
| Train school CCYS Coordinators and other school staff in survey administration | Not started |  |  |  |  |  |  | X | X | X |  |  |  |
| Administer CCYS, providing staffing support to schools as necessary | Not started |  |  |  |  |  |  |  |  |  | X | X |  |
| Monitor survey response | Not started |  |  |  |  |  |  |  |  |  | X | X | X |